## Slide 1
Project Management:
Process, Technology, and Practice
Ganesh Vaidyanathan
Chapter 4
Project Initiation

## Slide 2
Select projects
Project Manager (PM) Selection
Project Team
Stakeholder analysis
Requirement Gathering
Project Scope
Learning objectives

## Slide 4
1 Project Selection
Form upper management team
Identify, organize, and set criteria for all projects including financial and qualitative factors
Gather data on all projects
Estimate time and resources required
Analyze and decide on projects
Implement initial project plans

## Slide 5
1 Project Selection Process

## Slide 6
1 Screening of Projects

## Slide 7
Projects can be categorized as one of the following:
  Compliance: Projects that are essential to meet new requirements imposed by internal and external entities
    Internal entities may be executive management
    External entities may be government regulations and requirements
    “Must do” projects; if not implemented, may face penalties
  Emergency: Projects that are needed to meet emergency conditions; may be “must-do” projects; if not implemented, organizations may not be fully operational to fulfill their core competencies
1 Project Selection

## Slide 8
  Mission Critical: Critical to the mission of a company
    If not completed, would cause immediate, unacceptably negative impact to business
  Operational: Projects that are needed to support current operations
    Increase process efficiency
    Reduce product cost
    Improve performance and other metrics
  Strategic: Projects that are essential to support long-range mission (increase revenue, increase market-share)
1 Project Selection

## Slide 9
Provides the intellectual frameworks, conceptual models, and governing ideas that allow managers of an organization to identify opportunities for bringing value to customers and for delivering that value for a profit
The way an organization defines its business for a better future
  Organizations need to take advantage of the opportunities that projects represent.
Dynamically guides project actions and decision making as the project environment changes
  Projects need to be chosen and fielded to help achieve strategic intent. It is important to note that projects must deliver a product, service, or process that will provide the competitive advantage or value envisioned by the strategies of organizations.
1-b Project Strategy

## Slide 10
In many projects, value cannot be attained without the use of new technologies.
  Technology poses many risks and managers need to evaluate such perceived risks well before the beginning of projects.
  The skill requirements of using such technologies need to be analyzed before project initiation as well.
  All risks need to be evaluated for future projects in order to select the projects. Projects provide future opportunities and opportunities mean more uncertainty and greater risk.
1-b Project Strategy

## Slide 11
Project strategic value is defined as the impact a project will have on external entities like customers and suppliers.
Competitive differentiation may depend upon:
  Economies of scale
  Product differentiation
  Capital Requirements
  Access to distribution channels
  Cost disadvantages independent of scale
  Government policies
  Perceived competitive reactions in the market, and
  Price of organization’s products and services.
1-b Project Strategy and Value

## Slide 12
Value of a project can be determined by cash benefits (both magnitude and its timing).
  Magnitude and timing of cash benefits when compared to investments made on the projects have to be evaluated in project selection as well.
  If a project is not expected to bring some benefit to the organization, then there is no point in implementing this project.
1-b Project Strategy and Value

## Slide 13
1-b Scorecard analysis (Qualitative)

## Slide 14
A project charter is a document that formally recognizes a project, includes a problem statement, project objectives, benefits, process owners, and a project sponsor or a champion.
  Project purpose or justification
  Project objectives
  Project success criteria
  Project description
  Project risks at a high level
  Key milestones
  Budget information
1-c Project Charter

## Slide 15
  High level requirements of the project
  Project approval requirements
  Roles and responsibilities of the project manager and the project team
  Level of authority of the project manager
  Sponsor and authorizing persons of the project charter
1-c Project Charter

## Slide 16
The challenges for an organization to recruit effective project managers include:
  Ensuring that only qualified individuals are assigned to project management positions.
  Ensuring that an internal policy is designed, instituted, and followed to foster professional growth and development of such project management positions.
  Providing proper authority and accountability to project managers.
  Providing necessary management support.
  Ensuring that necessary resources are available for projects.
2- PM selection

## Slide 17
Personal
  Is honest and has integrity
  Assertive and confident
  Friendly and optimistic
  Enthusiastic and motivated
  Has a high energy level
  Has a sense of humor
Professional
  Able to work under uncertainty
  Adaptable to situations
  Well organized
  Understands business issues
2- PM characteristics

## Slide 18
Relational
  Team player
  Good written and oral communication skills
  Able to listen actively
  Able to present outcomes effectively
  Able to work effectively in teams
  Able to be a facilitator
  Respected by others
  Patient and shows perseverance
  Able to motivate and bring out the best in others
2- PM characteristics

## Slide 19
Satisfying end user and customer requirements
Performing flawlessly
Satisfying a myriad of technical performance criteria
Being user friendly and cost effective
Designing and implementing with quality
Providing great value to an organization, its suppliers, and its customers
Making sure that products are easily maintainable and services are easily accessible
2- PM Skills

## Slide 20
Ability to plan project activities effectively
Ability to schedule meetings, take copious notes, distribute meeting notes, and communicate effectively in meetings
Good people skills
Knows how to solve disputes
Knows how to deal with people from varied cultural and technology backgrounds
Knows how to motivate team members to achieve milestones
Ability to manage scope and ensure that the project scope does not grow beyond negotiated requirements
Great attitude and enthusiasm
2- PM qualifications

## Slide 21
Ability to manage change and exceptions in projects effectively
Ability to build teams
Ability to maintain stakeholder satisfaction, especially customer satisfaction
Ability to monitor and control all the six factors of success
Very familiar with financial and budgeting processes
Manages time well
Trained in project management principles
2- PM qualifications

## Slide 22
The size of a project team depends upon the size, the complexity, and the duration of a project.
The scope of a project will determine the composition of the team.
Technology employed in projects also determines the project team member selection.
High visibility projects with big budgets may involve project managers with many dedicated team members from various functions.
3- Project Team

## Slide 23
These big projects have to be equipped with team members with technical, functional, administrative, business, and financial skills.
  Functional skills include knowledge in various functions inside the organization as well as processes, practices, and procedures.
  Business skills may include contract management, marketing skills, financial, cost accounting, and other skills that are needed to run the business portion of a project.
3- Project Team

## Slide 24
Stakeholder characteristics
The positions that may be taken by the stakeholders that includes whether they are for or against the project
Level of interest of the stakeholders in the specific project
Level of influence of the stakeholders in the organization
Association of the stakeholders with the members of upper management
Potential alliances of stakeholders with other stakeholders
4- Stakeholder analysis

## Slide 25
Possible support by stakeholders for any changes in the project
Ability to affect the project policies through power and/or leadership
Ability to help the project team eliminate potential obstacles
Ability to help mitigate the project risks
4- Stakeholder analysis

## Slide 26
4- Stakeholder register
ID | Stakeholder | Roles and Expectations | Influence level | Level of Interest
A | Project Sponsor or Project Champion | CIO; Looks for value, profits, and ROI in projects; Expects that the project is beneficial to the firm | High | High
B | CFO | Looks for IRR payback and overall profits of the organization; Expects to meet the scope, budget, and schedule | High | Neutral
C | Functional Manager 1 | Looks for the most popular projects to allocate resources to; Expects to use resources efficiently | High | Neutral

## Slide 27
4- Stakeholder register
ID | Stakeholder | Roles and Expectations | Influence level | Level of Interest
D | Functional Manager 2 | Looks for the performance of the project; Interested in quality of the project | Neutral | Neutral
E | Customer 1 | Looks for the best value for the money | High | High
F | Customer 2 | Looks for the quality of the delivered project | Low | High
G | Users | Look for ease of use and doing their jobs with minimum effort | Neutral to high | High
H | Project Management Office | Policies have to be followed; CEO and CFO are in favor of the this office | High | High

## Slide 28
4- Stakeholder register
ID | Stakeholder | Roles and Expectations | Influence level | Level of Interest
J | Project Manager and Project Team | Young, energetic, and optimistic crew; PM is knowledgeable about project management techniques | High | High
K | Public | Does not care about this project; Not a very high-profile project | Low | Low

## Slide 29
A requirement is a capability of a system, product, or service to include the quantified and documented needs and expectations of the sponsor, customer, and other stakeholders
Tools used:
  Brainstorming
  Delphi technique
  Mind mapping
  Interviews, Focus Groups
  Facilitated workshops, and Nominal Grouping Technique
5- Requirements gathering

## Slide 30
Joint Application Design/Development (JAD) is a process used in prototyping to collect requirements while developing new information systems.
Joint Requirements Planning (JRP) is a structured group meeting of stakeholders to gather requirements by actively involving the stakeholders to replace individual interviews.
Document analysis is a technique used in creating requirements from “as-is” process documents.
5- Requirements gathering

## Slide 31
A use case is a technique used in software projects to document the potential requirements of a new system or software by conveying how the system should interact with the end user or another system to achieve a specific business goal graphically.
Interface analysis reviews various points where two or more systems interact with each other.
A prototype is a sample or a model built usually to test a concept, a process, a system, or a product.
5- Requirements gathering

## Slide 32
The Requirements Traceability Matrix is a table captured to map all the requirements of all stakeholders in order to track them until the project is complete.
5- Requirements gathering

## Slide 33
How much can be achieved in the current project?
When must the project be completed?
When and for how long will resources (people, facilities, equipment, etc.) be available?
Project scope description
Project acceptance criteria
Project deliverables
Project exclusions and constraints
Project assumptions
6- Project Scope
Scope creep: Scope creep is the addition of scope after it is defined in the scope document.

## Slide 34
Project initiation focuses on project selection and creation of project charters for selected projects.
Organizations usually prepare project proposals as the first means of starting a project. The proposal serves as an initial understanding document when selecting projects. These proposals will have a Statement of Work (SOW), the perceived benefits by year, estimated budgets needed by year, a high-level schedule request, and general information on the project being proposed.
Although every project begins with a proposal, not every proposal can, should, or does become a project. Due to limited resources, choices in projects have to be made.
Summary